## Sheet1
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US_02 | T_01 | Build OCR extraction module | 2025-09-01 | 2025-09-03 | Ravi | Development | Completed | 8 | Day 1: Done
US_02 | T_02 | Fine-tune NLP model for address verification | 2025-09-03 | 2025-09-06 | Sneha | Model Training | Completed | 12 | Day 1: Done; Day 2: Done; Day 3: Done
US_02 | T_03 | Train CNN model to detect document tampering | 2025-09-06 | 2025-09-09 | Bhanu | Model Training | Completed | 10 | Day 2: Done; Day 3: Done; Day 4: Done; Day 5: Done
US_02 | T_04 | Train GNN model to detect duplicate Aadhaar identities | 2025-09-09 | 2025-09-12 | Arjun | Research/Implementation | Completed | 14 | Day 3: Done; Day 4: Done; Day 5: Done; Day 6: Done; Day 7: Done; Day 8: Done
US_02 | T_05 | Validate models and compare accuracy | 2025-09-12 | 2025-09-14 | Team | Testing | Completed | 6 | Day 7: Done; Day 8: Done; Day 9: Done; Day 10: Done; Day 11: Done