## Sheet1
SL | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 4 | 2025-09-20 | 2025-10-04 | Group A – Backend | Start writing modularized APIs | Stop skipping documentation | Continue collaborating across frontend-backend | Created proper README & module docstrings
2 | Sprint 4 | 2025-09-20 | 2025-10-04 | Group A – Frontend | Start using responsive UI components | Stop making UI directly from backend responses | Continue improving user-friendly dashboards | Added validation screens & error messages
3 | Sprint 4 | 2025-09-20 | 2025-10-04 | Group B – Backend | Start containerizing deployment | Stop using local JSON for AML data | Continue focusing on clean code | Created Docker container for backend
4 | Sprint 4 | 2025-09-20 | 2025-10-04 | Group B – Frontend | Start implementing toast notifications | Stop using hardcoded endpoints | Continue enhancing UX | Improved navigation and visual consistency